{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["实施项目完成情况（系统）"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"实施项目完成情况（系统）","index":0,"n_rows":92,"n_cols":7,"rows_kept":92,"merged":[[0,0,0,6]],"flags":["formulas_cached_only"]}
["揭西县2023年衔接资金项目完成情况"]
["序号","镇","项目名称","资金类型","分配资金（万元）","项目完成情况","备注"]
[1,"凤江镇","2023年度凤江镇东新村委溪顶溪下村道建设项目","中央财政衔接推进乡村振兴补助资金",48,"已完成"]
[2,"凤江镇","2023年度凤江镇洪湖村委潭口上堤路建设项目","中央财政衔接推进乡村振兴补助资金",22,"已完成"]
[3,"河婆街道","2023年河婆街道庙垅村委旁主巷道硬底化及配套工程","中央财政衔接推进乡村振兴补助资金",40,"已完成"]
[4,"河婆街道","2023年河婆街道下滩村五联、群丰、寨肚等主巷道硬底化及排水改造工程","中央财政衔接推进乡村振兴补助资金",20,"已完成"]
[5,"灰寨镇","2023年灰寨镇后洋斜坡路下至后洋岭完村灌溉水沟项目","中央财政衔接推进乡村振兴补助资金",50,"已完成"]
[6,"金和镇","2023年金和镇金光村寨前公共场地硬底化建设项目","中央财政衔接推进乡村振兴补助资金",40,"已完成"]
[7,"金和镇","2023年金和镇南联小学学校前道路改造提升项目","中央财政衔接推进乡村振兴补助资金",20,"已完成"]
[8,"良田乡","2023年度良田乡金坑村山尾机耕路建设工程","中央财政衔接推进乡村振兴补助资金",50,"已完成"]
[9,"龙潭镇","2023年龙潭镇双龙村基础设施建设工程","中央财政衔接推进乡村振兴补助资金",37,"已完成"]
[10,"龙潭镇","2023年龙潭镇龙东村仓下楼至老屋下道路建设工程","中央财政衔接推进乡村振兴补助资金",25,"已完成"]
[11,"钱坑镇","2023年钱坑镇顶联村叶下桃巷道硬底化工程","中央财政衔接推进乡村振兴补助资金",4,"已完成"]
[12,"上砂镇","2023年上砂镇活动大桥至新岭村冷水井的主干道路灯安装工程","中央财政衔接推进乡村振兴补助资金",40,"已完成"]
[13,"上砂镇","2023年上砂镇竹苏村太阳能路灯安装工程","中央财政衔接推进乡村振兴补助资金",10,"已完成"]
[14,"塔头镇","2023年塔头镇大山脚自然村村道硬底化工程项目","中央财政衔接推进乡村振兴补助资金",40,"已完成"]
[15,"塔头镇","2023年塔头镇濂溪自然村沟渠三面光工程","中央财政衔接推进乡村振兴补助资金",12,"已完成"]
[16,"五云镇","2023年五云镇石陂村水利建设项目","中央财政衔接推进乡村振兴补助资金",29.5,"已完成"]
[17,"大溪镇","2023年度大溪镇大园村深光自然村停车场及路灯项目","中央财政衔接推进乡村振兴补助资金",22.244683,"已完成"]
[18,"大溪镇","2023年大溪镇大园村顶光自然村路灯项目","中央财政衔接推进乡村振兴补助资金",10.62893,"已完成"]
[19,"大溪镇","2023年大溪镇大光村大堀寨自然村停车场及路灯项目","中央财政衔接推进乡村振兴补助资金",22.215808,"已完成"]
[20,"大溪镇","2023年大溪镇后洋村建设光伏发电项目","中央财政衔接推进乡村振兴补助资金",30,"已立项"]
[21,"大溪镇","2023年大溪镇金星村雨污分流及相关建设工程-大寮、汕头自然村(续建项目)","省级衔接资金",95,"已完成"]
[22,"大溪镇","2023年大溪镇金星村雨污分流及相关建设工程-大路顶、渔福自然村(第二期续建项目)","省级衔接资金",42,"已完成"]
[23,"大溪镇","2023年揭西县大溪镇规划优化提升地形图测绘项目","省级衔接资金",53,"已完成"]
[24,"东园镇","2023年东园镇炉清村寨前东路及挡土墙项目","中央财政衔接推进乡村振兴补助资金",62.43901400000016,"已完成"]
[25,"东园镇","东园镇赤岩村投资东园镇硕丰家禽饲养场","中央财政衔接推进乡村振兴补助资金",30,"已开工"]
[26,"东园镇","2023年度东园镇古福村雨污分流工程建设项目","省级衔接资金",250,"已完成"]
[27,"东园镇","2023年度东园镇赤岩村（二期）雨污分流工程建设项目","省级衔接资金",172,"已完成"]
[28,"河婆街道","南新村壮大村集体经济光伏发电项目","中央财政衔接推进乡村振兴补助资金",30,"已立项"]
[29,"灰寨镇","2023年度河棉公路灰寨镇老宫林至灰龙路段市政消火栓工程","省级衔接资金",20,"已完成"]
[30,"灰寨镇","2023年度灰寨镇新图村投资揭西县泉植园林有限公司项目","中央财政衔接推进乡村振兴补助资金",30,"已完成"]
[31,"京溪园镇","2023年度京溪园镇岭溪村委京溪园村下堂路硬底化建设工程","中央财政衔接推进乡村振兴补助资金",10.360043,"已完成"]
[32,"京溪园镇","2023年京溪园镇长滩村委祠堂下村公共停车场建设工程","中央财政衔接推进乡村振兴补助资金",17.759447,"已完成"]
[33,"京溪园镇","2023年度京溪园镇曾大寮村大坑洋机耕路建设工程","中央财政衔接推进乡村振兴补助资金",13.067644,"已完成"]
[34,"京溪园镇","2023年度京溪园镇美德村洋心机耕路建设工程","中央财政衔接推进乡村振兴补助资金",19.450329,"已完成"]
[35,"良田乡","良田乡投资广东大洋茶业有限公司项目","中央财政衔接推进乡村振兴补助资金",30,"已完成"]
[36,"良田乡","2023年度良田乡岸洋村西岸线路基建设工程","省级衔接资金",65,"已完成"]
[37,"良田乡","2023年度良田乡岸洋村西大线路基建设工程","省级衔接资金",50,"已完成"]
[38,"良田乡","2023年度良田乡金坑村金古线路基建设工程","省级衔接资金",95,"已完成"]
[39,"良田乡","2023年度良田乡下村南方人民银行纪念馆广场红色提升工程","省级衔接资金",10,"已完成"]
[40,"良田乡","2023年度良田乡桐树坪村桐树坪小学提升工程","省级衔接资金",12,"已完成"]
[41,"良田乡","2023年度良田乡岸洋村岸洋小学提升工程","省级衔接资金",8,"已完成"]
[42,"良田乡","2023年度良田乡金坑村坪上小学提升工程","省级衔接资金",15,"已完成"]
[43,"良田乡","2023年度良田乡岸洋村文化室建设工程","省级衔接资金",15,"已完成"]
[44,"良田乡","2023年度良田乡综合性文化服务中心提质增效项目","省级衔接资金",12,"已完成"]
[45,"龙潭镇","2023年龙潭镇双龙村购置商铺项目","中央财政衔接推进乡村振兴补助资金",30,"已立项"]
[46,"龙潭镇","2023年龙潭镇泉水塘村巷道硬底化工程项目","省级衔接资金",21,"已完成"]
[47,"龙潭镇","2023年龙潭镇菜仔园村巷道硬底化工程项目","省级衔接资金",28,"已完成"]
[48,"龙潭镇","2023年龙潭镇陂尾村上圩松林埔道路硬底化等基础设施建设项目","省级衔接资金",40,"已完成"]
[49,"龙潭镇","2023年龙潭镇龙跃村天昌楼片公共活动场所建设项目","省级衔接资金",70,"已完成"]
[50,"龙潭镇","2023年龙潭镇双龙圳井下段渠道农田水利建设项目","省级衔接资金",45,"已完成"]
[51,"棉湖镇","2023年棉湖镇上浦村农田灌溉站提升项目","中央财政衔接推进乡村振兴补助资金",15.738849,"已完成"]
[52,"棉湖镇","2023年棉湖镇贡山村新桥头至坛仔尾桥道路硬底化工程","中央财政衔接推进乡村振兴补助资金",43.830148,"已完成"]
[53,"棉湖镇","棉湖镇上浦村新建商铺项目","中央财政衔接推进乡村振兴补助资金",30,"已完成"]
[54,"棉湖镇","2023年度棉湖镇甲埔村综合市场北部片区雨污分流及道路硬底化工程","省级衔接资金",55,"已完成"]
[55,"棉湖镇","2023年度棉湖镇上浦村工业区片区雨污分流项目","省级衔接资金",90,"已完成"]
[56,"棉湖镇","2023年度棉湖镇境潭村村道硬底化建设工程","省级衔接资金",90,"已完成"]
[57,"棉湖镇","2023年度棉湖镇玉石村油甘精加工项目","省级衔接资金",50,"已完成"]
[58,"棉湖镇","2023年度棉湖镇贡东村西区巷道硬底化工程项目","省级衔接资金",70,"已完成"]
[59,"南山镇","2023年南山镇上寮村道路硬底化及配套设施工程","中央财政衔接推进乡村振兴补助资金",28.565689,"已完成"]
[60,"南山镇","2023年南山镇西友村道路硬底化及配套设施工程","中央财政衔接推进乡村振兴补助资金",31.438756,"已完成"]
[61,"南山镇","2023年南山镇上寮村投资揭西县鸿霖蔬菜种植专业合作社","中央财政衔接推进乡村振兴补助资金",30,"已立项"]
[62,"坪上镇","2023年度石峡村黄柯路改造工程","中央财政衔接推进乡村振兴补助资金",12.004276,"已完成"]
[63,"坪上镇","2023年度潭角村机耕路硬底化工程","中央财政衔接推进乡村振兴补助资金",10.311391,"已完成"]
[64,"坪上镇","2023年度坪上镇农产品加工厂房建设项目","中央财政衔接推进乡村振兴补助资金",49.692262,"已完成"]
[65,"坪上镇","坪上镇红旗村投资广东霖甜食品科技有限公司","中央财政衔接推进乡村振兴补助资金",30,"已立项"]
[66,"钱坑镇","2023年钱坑镇埔龙尾村水利设施涵洞工程","中央财政衔接推进乡村振兴补助资金",9.236104,"已完成"]
[67,"钱坑镇","2023年钱坑镇埔龙尾村委坛仔坡机耕路硬底化工程","中央财政衔接推进乡村振兴补助资金",9.878654,"已完成"]
[68,"钱坑镇","2023年钱坑镇白石村龙山路硬底化工程","中央财政衔接推进乡村振兴补助资金",41.670718,"已完成"]
[69,"钱坑镇","2023年钱坑镇白石村光伏发电项目","中央财政衔接推进乡村振兴补助资金",30,"已立项"]
[70,"钱坑镇","2023年钱坑镇顶联村雨污分流工程建设项目","省级衔接资金",100,"已完成"]
[71,"钱坑镇","2023年钱坑镇竹园内村雨污分流工程建设项目","省级衔接资金",110,"已完成"]
[72,"上砂镇","上砂镇竹苏村2023年扶持壮大村级集体经济项目","中央财政衔接推进乡村振兴补助资金",30,"已立项"]
[73,"塔头镇","投资揭西县龙锦种养专业合作社","中央财政衔接推进乡村振兴补助资金",30,"已完成"]
[74,"五经富镇","2023年五经富镇文联村背头段机耕路建设项目","中央财政衔接推进乡村振兴补助资金",49.416117,"已完成"]
[75,"五经富镇","五经富镇朝阳村建设发电光伏项目","中央财政衔接推进乡村振兴补助资金",30,"已立项"]
[76,"五经富镇","2023年五经富镇新安雨污分流工程","省级衔接资金",42,"已完成"]
[77,"五经富镇","2023年五经富镇五新村雨污分流工程","省级衔接资金",28,"已完成"]
[78,"五云镇","2023年五云镇流坪村水利建设项目","中央财政衔接推进乡村振兴补助资金",19.28,"已完成"]
[79,"五云镇","2023年五云镇下洞村水利建设项目","中央财政衔接推进乡村振兴补助资金",13.271138,"已完成"]
[80,"五云镇","五云镇流坪村投资揭西县金岭生猪屠宰有限公司项目","中央财政衔接推进乡村振兴补助资金",30,"已立项"]
[81,"坪上镇","2023年度坪上镇中小学教室照明改造工程","省级衔接资金",60,"已完成"]
[82,"坪上镇","2023年度坪上镇绵基中学沥青跑道建设工程","省级衔接资金",62,"已完成"]
[83,"东园镇","2023年度东园镇赤岩村白木城、新兴、赤岩、柑园自然村村道硬底化建设工程项目","省级衔接资金",47,"已完成"]
[84,"东园镇","2023年度东园镇古福村口寨自然村村道改造提升工程","省级衔接资金",69,"已完成"]
[85,"上砂镇","2023年度上砂镇双丰村自然村内道路硬底化工程","省级衔接资金",49,"已完成"]
[86,"上砂镇","2023年度上砂镇下联村坡坑大深进护坡建设工程","省级衔接资金",40,"已完成"]
[87,"上砂镇","2023年度上砂镇北湖村自然村内道路硬底化工程","省级衔接资金",42,"已完成"]
[88,"上砂镇","2023年度上砂镇下联村付坑自然村雨污分流工程建设项目二期工程","省级衔接资金",40,"已完成"]
[89,"南山镇","2023年南山镇分水村道路硬底化及配套设施工程","省级衔接资金",23,"已完成"]
[90,"灰寨镇","2023年度灰寨镇上角村公共休闲场所建设及农田水利沟渠建设工程","省级衔接资金",34,"已完成"]