{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["项目安排"],"read":"whole","date_system":"1900"}

{"sheet":"项目安排","index":0,"n_rows":12,"n_cols":12,"rows_kept":12,"merged":[[1,0,1,11],[2,0,2,4],[2,9,2,11],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[3,9,4,9],[3,10,4,10],[3,11,4,11],[5,0,5,5]]}
["附件2:"]
["揭西县2025年中央财政衔接推进乡村振兴补助资金项目完成情况表"]
["填报单位：揭西县乡村振兴局",{"$nulls":8},"单位：万元"]
["序号","县","镇","村","项目名称","项目类型","项目计划投入（万元）","安排资金（万元）","实施主体","建设任务\n（概要描述）","绩效目标\n（概要描述）","完成情况"]
[{"$nulls":7},"安排资金"]
["合计",{"$nulls":5},{"$f":"SUM(G7:G35)","v":{"v":159.5,"d":"159.50"}},{"$f":"SUM(H7:H35)","v":{"v":136,"d":"136.00"}}]
[1,"揭西县","大溪镇","大溪镇井新村","2025年大溪镇井新村两坝机耕路建设项目","公共基础设施",{"v":30,"d":"30.00"},{"v":30,"d":"30.00"},"大溪镇政府","道路全长401米，设计宽度4米，厚度0.18米，C30混凝土，工程量1604平方米，同时，内侧设置断面0.25*0.3截洪沟289米。","通过道路硬底化及配套设施，提升人居环境，改善交通条件，方便群众出行。","已完成"]
[2,"揭西县","金和镇","金新村委","揭西县金和镇金新村委油寮村四、五片机耕路路面硬底化项目","公共基础设施",{"v":20,"d":"20.00"},{"v":20,"d":"20.00"},"金新村委会","资金用于对金新村委油寮村四、五片机耕路路面硬底化建设，长356米，宽3米，厚度15厘米，并对沟墙356米进行改造。","通过实施金和镇金新村委油寮村四、五片机耕路路面硬底化项目，达到提高农业生产效率，降低农业生产成本，促进农业机械化的发展的目标。","已完成"]
[3,"揭西县","金和镇","和西村委","揭西县金和镇和西村委老寨村寨机耕路硬底化建设项目","公共基础设施",{"v":25,"d":"25.00"},{"v":25,"d":"25.00"},"和西村委会","资金用于对和西村老寨村寨前片农田机耕路进行硬化，长506米，宽4米，厚度15厘米。","通过实施金和镇和西村委老寨村寨机耕路硬底化建设项目，达到提高农业生产效率，降低农业生产成本，促进农业机械化的发展的目标。","已完成"]
[4,"揭西县","河婆街道","下滩村","2025年河婆街道下滩村横北线灌溉渠支流黄牛寮段提升工程","公共基础设施",31,31,null,"对下滩村横北线灌溉渠支流黄牛寮段水利渠进行清淤及三面光，总长约1000米，宽0.6米。","通过实施2025年河婆街道下滩村横北线灌溉渠支流黄牛寮段提升工程，提升村水利灌溉能力，保障村民耕地用水的目标，改善下滩村及后埔村约700亩耕地的灌溉用水，受益群众满意度≥90%","已完成"]
[5,"揭西县","五云镇","下硿村","五云镇下硿村委下埔村灌溉工程","公共基础设施",{"v":35,"d":"35.00"},{"v":13,"d":"13.00"},"五云镇政府","拟对该水利灌溉渠道进行维修加固，该水渠长597米，工程项目主要对水渠进行清淤、加固，部分沟底进行批荡，损毁段做三面光和加盖板。","项目建成后，方便210亩农田灌溉，惠及约1000多人的农业生产。","已完成"]
[6,"揭西县","五云镇","石陂村","五云镇石陂村下禾沟段河堤砌筑工程（二期）","公共基础设施",{"v":18.5,"d":"18.50"},{"v":17,"d":"17.00"},"五云镇政府","该项目计划建设下河沟段河堤新建砌毛石挡土墙，该工程总长约73.5米，墙身高度2米，基础宽度2.5米*高度0.8米。","项目建成后可有效地防止水流冲刷岸边的土壤，保护沿岸农田道路的安全。","已完成"]